## Slide 1: Simulation and exploration of Thz TRNASMISSION LINES
Name: Mohammed AlShuaili
ID: 20106181
Supervisor: Dr Marissa Condon

## Slide 2: Problem Description
The Challenge: Efficiently model THz transmission lines considering high attenuation, dispersion, and non-linearities.
Why It's Important: Key to enabling technologies like 6G, high-speed communication, and biomedical imaging.

## Slide 3: Proposed Solutions
Objective: Develop accurate, efficient numerical model.
FDTD: Initial time-domain approximation.
RLC Ladder Models: Discretization for computational efficiency.
NILT: Numerical transformation for validation and accuracy.

## Slide 4: Work Progress
Completed Tasks:
- Implemented FDTD for lossless lines in MATLAB.
- Simulated RLC ladder networks; validated accuracy with different section counts.
- Applied NILT for s-domain solutions.
Results:
- FDTD and RLC ladder methods show promising accuracy.
- Challenges with optimizing section counts for computational efficiency.
[Placeholder for visual/image]

## Slide 5: Project Plan for Semester 2
Week 1-3: Validate and refine models using s-domain and time-domain techniques.
1
Week 4-7: Test models at varying THz frequencies and derive equivalent time-domain representation.
2
Week 8-10: Investigate PSPICE simulations; finalize report.
3

## Slide 6: Key Challenges and Mitigation
Challenges:
Deriving a time-domain model to match s-domain solutions AWE.
Validating the model across wide frequency.
Mitigation:
Optimize RLC ladder sections for efficiency.
Use iterative testing and error analysis to refine the model.

## Slide 7: Conclusion and Future Plans
Achievements:
- Progress in modeling approaches; validated results demonstrate feasibility.
Next Steps:
- Extend models for complex THz systems; explore real-world applications.

## Slide 8: References